## in flight
Product tracker
Kept by Ana Fialho. Updated when someone remembers.
Item | What | Type | Status | Owner | Opened | Last touched | Notes
OPPORTUNITY-04 | Expand the portal rollout | opportunity | Open | Ana Fialho | 2026-06-18 | 2026-08-13 | Brief written in June, not revised since
DECISION-0028 | Extend pilot scope to 28 accounts | decision | done | Ana Fialho | 2026-08-07 | 2026-08-07 | Recorded as a scope change
DECISION-0031 | Deprecate legacy cycle count module | decision | DONE | Ana Fialho | 2026-07-22 | 2026-07-22 | Review due 2026-11-01
EXPERIMENT-02 | Pilot experiment | experiment | closed | Ana Fialho | 2026-05-28 | 2026-07-21
BLOCKER-01 | POLICY-03 sign-off for LATAM accounts | blocker | open |  | 2026-07-11 | 2026-08-22 | Asked three times
REQUEST-G01 | Use pilot numbers in renewals | request | Open | Gabriela Rocha | 2026-08-05
REQUEST-R01 | Fix review queue before widening | request | open | Rui Bastos | 2026-08-08 |  | Not reflected in the brief
REQUEST-T01 | LATAM transfer basis | request | open | Tomas Silva | 2026-08-11 |  | Same as BLOCKER-01
REQUEST-A01 | Decide by end of August | request | open | Ana Fialho | 2026-08-13 |  | Now overdue
LAUNCH-01 | Launch readiness assessment | task | In Progress | Ana Fialho | 2026-08-19 | 2026-08-26 | Three rows still No
ADOPT-01 | Agree adoption measures | task | open | Ana Fialho | 2026-08-20 |  | Draft only
REV-01 | Review DECISION-0031 migration progress | task | not started |  |  |  | Due 2026-11-01